## Milestones
Milestone Project
Project Name | PIC | Milestone Name |  |  | Target | Milestone Weighted |  |  | Milestone Achievement
[5 empty] | Date |  | Nov | Dec
Enterprise Risk Management | Developer | Pre-Project
|  |  | Feasibility study |  | Nov | 2% |  |  | 0%
|  |  | Setup Project |  | Nov | 2% |  |  | 0%
Authentication
|  |  | Modul Login |  | Nov | 3% |  |  | 0%
|  |  | Modul Reset password |  | Nov | 3% |  |  | 0%
Dashboard
|  |  | Modul Dashboard |  | Dec | 3% |  |  | 0%
|  |  | View Summary |  | Dec | 3% |  |  | 0%
|  |  | View Graph |  | Dec | 3% |  |  | 0%
Menu Risk Register
|  |  | Modul Input RR |  | Dec | 3% |  |  | 0%
|  |  |  | Input RR | Dec | 3% |  |  | 0%
|  |  |  | Mitigasi Plan | Dec | 3% |  |  | 0%
|  |  |  | Pelaporan & Evaluasi | Dec | 2% |  |  | 0%
|  |  | Modul Report |  | Dec | 3% |  |  | 0%
|  |  |  | HeatMap | Dec | 3% |  |  | 0%
|  |  |  | Detail Information | Dec | 2% |  |  | 0%
Menu Search Engine
|  |  | Modul Search |  | Dec | 3% |  |  | 0%
|  |  | Search Filter |  | Dec | 3% |  |  | 0%
|  |  | View Search Result |  | Dec | 3% |  |  | 0%
Menu Report
|  |  | Modul Report |  | Dec | 3% |  |  | 0%
|  |  | Filter Report |  | Dec | 3% |  |  | 0%
|  |  | View Report |  | Dec | 3% |  |  | 0%
|  |  | Export Report |  | Dec | 3% |  |  | 0%
Menu Repository
|  |  | Modul Repository |  | Dec | 3% |  |  | 0%
|  |  | View Data/File Repository |  | Dec | 3% |  |  | 0%
|  |  | Upload & Download File |  | Dec | 3% |  |  | 0%
Menu Risk Event
|  |  | Modul Risk Event |  | Dec | 3% |  |  | 0%
|  |  | View Risk Event |  | Dec | 3% |  |  | 0%
|  |  | Input Data Risk Event |  | Dec | 3% |  |  | 0%
Menu Risk Universe
|  |  | Modul Risk Universe |  | Dec | 3% |  |  | 0%
|  |  | View Risk Universe |  | Dec | 3% |  |  | 0%
Menu Risk Governance
|  |  | Modul Risk Governance |  | Dec | 3% |  |  | 0%
|  |  | View Risk Governance |  | Dec | 3% |  |  | 0%
Menu Administrator
|  |  | Modul User Management |  | Dec | 3% |  |  | 0%
|  |  | Modul user Privilage |  | Dec | 3% |  |  | 0%
|  |  | Modul Unit Management |  | Dec | 3% |  |  | 0%
|  | User Acceptance Test |  |  | Dec | 2% |  |  | 0%
| TOTAL |  |  |  |  | 100% |  |  | 0%